## Sheet1
Activity Number | Activity Name | Activity Name Description | Number of Days | Start Date | Dependencies | Milestones
1 | SYSADD 1&2 | Fullfillment of requirements in Sysadd | 60 | 21-09-16
1.2 | Team Meeting | Initial team meeting | 1 | 21-09-16
1.3 | Client Meeting | Initial Client Meeting | 1 | 21-09-16
1.4 | Project Charter | Accomplishment of Project Chater | 7 | 21-09-16 |  | charter
1.5 | SWOT Analysis | Analyzation of SWOT | 2 | 28-09-16 |  | SWOT table
1.6 | Use Case Diagram | creation of Usecase Diagram | 7 | 30-09-16 |  | usecase diagram
1.7 | Context Diagram | creation of context diagram | 5 | 30-09-16 |  | context diagram
1.8 | Functional Requirements | listing of FR | 7 | 2016-05-10 |  | list of FR
1.9 | Non-Functional Requirements | listing of NFR | 7 | 2016-05-10 |  | list of NFR
1.1 | Class Diagram | creation of Class Diagram | 3 | 2016-11-10 |  | Class Diagram
1.11 | Object Diagram | creation of Object Diagram | 3 | 2016-11-10 |  | Object Diagram
1.12 | Data Flow Diagram | creation of DFD | 3 | 2016-11-10 |  | DFD
1.13 | Entity Relationship Diagram | creation of ERD | 7 | 14-10-16 |  | ERD
1.14 | Structure Charts | produce Structure Charts | 6 | 14-10-16 |  | Chart
1.15 | Sequence Diagram | produce Sequence Diagram | 7 | 19-10-16 |  | Sequence Diagram
1.16 | State Transition Diagram | create State Transition Diagram | 8 | 19-10-16 |  | ST Diagram
1.17 | Component Diagram | create Component Diagram | 10 | 26-10-16 |  | Component Diagram
1.18 | Composite Structure Diagram | create Compsite Structure Diagram | 4 | 2016-07-11 |  | Composite Structure
1.19 | Hierchial Input Process Output | make Hierchial Input Process Output | 10 | 2016-07-11 |  | HIPO
1.2 | Activity Diagram | create Activity Diagram | 8 | 2016-07-11 |  | Activity Diagram
1.21 | Screen Layout | producw Screen layout | 7 | 15-11-16 |  | Screenn Layout
1.22 | Event Tables | make event tables | 8 | 15-11-16 |  | Event table
1.23 | Decision Tables | make decision tables | 8 | 15-11-16 |  | decision table
1.24 | Deployment Diagram | make deployment diagram | 4 | 22-11-16 |  | deployment diagram
1.25 | Test Plan | make test plan | 4 | 22-11-16 |  | test plan
1.26 | Communication Diagram | create communication diagram | 7 | 26-11-16 |  | communication diagram
1.27 | Interaction Overview Diagram | create interaction overview diagram | 7 | 26-11-16 |  | Interaction overview
1.28 | Architechture Interconnect Diagram | create architechture interconnect diagram | 7 | 26-11-16 |  | Architechture Interconnect Diagram
1.29 | Timing Diagram | create timig diagram | 7 | 26-11-16 |  | Timing Diagram
1.3 | Prototype Status Report | status report | 7 | 2016-02-12 |  | status report
1.31 | Test Result | organization of result | 7 | 2016-09-12 |  | Test Result
1.32 | Presentation | project presentation | 1 | 14-12-16 |  | feedback
1.33 | Finalization of Documents | finalization of documents | 3 | 18-12-16 |  | final document
2 | CSPROJ | Fullfillment of requirements in CSPROJ | 60 | 2017-11-01
2.1 | Project update | uploading of sysadd files to csproj | 1` | 15-1-17 | SYSADD Document
2.2 | Activity List | Listing of Activities to be done in CSPROJ | 3 | 20-1-17
2.3 | RFP/SOW | Release of RFP/SOW | 1 | 22-1-17
2.4 | Design | System Design Plan | 7 | 25-1-17
2.5 | Implementation | System Implementation Plan | 7 | 23-1-17
2.6 | develop | Develop Server Application | 30 | 25-1-17
2.6.1 | GUI | Develop User Interface | 7 | 25-1-17
2.6.2 | xyz | Develop XYZ Interface | 7 | 2017-01-02
2.6.3 | Server | Procure Server | 7 | 2017-05-02
2.6.4 | Workstation | Procure WorkStation | 7 | 2017-05-02
2.6.5 | Database | Procure Databas | 7 | 2017-05-02
2.6.6 | UI Tools | Procure User Interface Building Too | 7 | 2017-11-02
2.6.7 | OS | Procure Operating System | 7 | 2017-11-02
2.6.8 | Integration | Perform Integration Testing | 7 | 19-2-17
2.6.9 | Conversation | Develop Conversation Plan | 7 | 2017-05-03
2.6.10 | Manual | Develop User Manual | 3 | 2017-12-03
2.6.11 | Transition Management | Transition Management | 7 | 2017-12-03
2.7 | Completion | Project Completion | 7 | 15-3-17 | Fully developed System
2.8 | Closure | Project Closure | 3 | 18-3-17 | Signed Contract
2.9 | Documentation | Finalization of Documents | 3 | 18-3-17 | Final Docu for presentation
2.1 | Presentation | Presentation | 1 | 20-3-17